## Slide 1
Practice Launch Process

## Slide 2
Agenda
Review the process
Review/assign program kick off responsibilities
Review/assign ongoing program responsibilities
Review/agree onsite launch agenda
Next Steps

## Slide 3
The Process
Outbound Call
Reception
Schedule Appointment
Email Prep
Send Reminders
Schedule Patients
Conduct Intake and Review (~60 minutes)
Patient Arrives (or answers phone)*
Conduct
AWV & Adv Directives
Review Report with Patient*
Schedule Follow Ups*
Submit for Reimbursement
Getting Ready
Update EMR
BP: At check In, hand out AWV “prescription” page
BP: At check out: Schedule Visit
Add to EMR
Add to Scheduling Tool
Use Content from Hand-Out
Use Content from Hand-Out
BP: Rule of 3’s
Use Outbound Call Scripts
BP: W/Th, 8-12 & 4-6
Add new meds
Update contact info
Enter coding information
Append files if needed
Post Appointment
Set Up Practice and Users
Train Staff
Load Patients (optional)
Prep Practice
*When intake is conducted via telephone, the report review is completed by a Physician in a follow up appointment, and the follow ups are then scheduled with front desk staff or in the E.H.R if the practice allows a third party to schedule.
BP=Best Practice
90-minute appointments in case of overruns

## Slide 4
Program Kick-Off Responsibilities
Activities | Defined | MCW Responsibility | Partner Responsibility (MCW if partner not available) | Practice Responsibility
 | Company, Practices, and Users set up on the MCW platform, accessed at www.mycareware.com, on the Account Access page. | Respond as needed. | Assist practice Admin. | Define the Admin who will manage the account, set up practices, and then invite users to create accounts.
OPTIONAL | Patient Data Extraction Pull patient data into excel or CSV files and upload to secure link *Why optional: patients can be set up as scheduled. Uploading patient data makes the intake faster. | Map secure files to system and upload. Completion time: up to 10 days. | Assist practice. | Pull data and upload files. Or provide partner with EMR access.
 | Staff Training Assign roles and train on best practices, new processes (if needed), and use of platform | Provide scheduled group or 1:1 training for system users Admin AWV intake | Provide scheduled group or 1:1 training Schedulers Front desk | Assure staff ready: confusion and lack of prep can create bad patient experiences
 | Review Protocols & Referrals for: Elder Mistreatment; Extreme Vitals; Cognitive Impairment; High Risk Depression; Not Taking Meds as Prescribed; Visibly Unwell; Any other issue of concern where a patient should be seen urgently | None | None | Practice adds to training as needed
 | Confirm EMR has these codes ready G0402, G0438, G0439, G0468, G0513, G0514, 99497-M, 99498-M *We will also provide Z-codes and CPTII codes where the AWV meets the qualification. | None | None | Assign staff to review and update as needed.
Set Up Practice and Users
Load Patients
Train Staff
Prep Practice
PROTOCOLS
Prep Practice
EMR Codes

## Slide 5
On-Going Process Practice Roles
Activities | Sample Documents at www.mycareware.com | Responsibility | When
Include “prescription” paperwork with every Medicare patient | Sample in AWV Tools AWV Prescription Form | Reception/Front Desk | At check in
Prescribe AWV for patients | Sample in AWV Tools AWV Prescription Form | Physicians Advanced Practitioners | At end of E&M appointments
Schedule patients who are in the office | Sample in AWV Tools AWV Prescription Form | Reception/Front Desk | At check out
Outbound call to schedule patients | Sample in AWV Tools Marketing Tools Content | Scheduling team or Call Center or Person who will conduct the intake | Recommended: Wed/Thurs, 8-12am or 4-6pm (Studies show: best days & times to reach people
Send all reminders |  | Use EMR or send manually | 3-3-3 (3 weeks, 3 days, 3 hours prior to appt) Studies show: best cycle to keep no-shows low
Conduct Intake | Practice Portal | M/A or Outsource Partner | 
Conduct Report Reviews | Sample Reports in AWV Tools Actual Reports in the Practice Portal | M/A, Nurse, AP, or Physician | 
Update Critical Elements in E.H.R. | Sample Reports in AWV Tools Actual Reports in the Practice Portal | Person who conducted intake or Outsource Partner | Immediately following appointment
Submit for Reimbursement | Sample Reports in AWV Tools Actual Reports in the Practice Portal | Billing/RCM team | Same day as completion
Schedule Follow Ups |  | Reception/Front Desk or Outsource Partner | At check out; or if telehealth, either outreach or at next onsite appointment

## Slide 6
Sample One Day Training and Launch Agenda
Topic | Time | Who Typically | Comments | Sample Tools at www.mycareware.com
All Staff Overview | 15 min | All Staff breakfast or end of day…or send out email with attachments…or capture as groups trained below | Handout or send email to all staff with attachment for review | Sample in AWV Tools Patient FAQs (DIY or White Glove)
Reception Role & Handouts | 15 min | Reception Staff | Patient Handout | Sample in AWV Tools AWV Prescription Form
Scheduling Process: Reception | TBD | Reception and/or Scheduling Staff | Handling scheduling, cancellations and reschedules | 
Scheduling Process: Schedulers | 30 min | Practice Manager Schedule Coordinator Scheduling Company | Keeping EMR and MCW in sync with initial schedule date | Sample in AWV Tools Marketing Tools
Coding & Reimbursement | 15 min | Practice Managers Billers/Billing Company | Assigning email to superbill | Sample in AWV Tools Coding
Application Use | 3 hours | Test Administrators | Confirm Sign On Review and practice | Use Test Practice to Run AWVs – set up one new patient; run on an existing patient
Physician Training | LUNCH or END OF DAY | Physicians Advanced Practitioners | Can do more or less depending on physician desire/time | Sample in AWV Tools Coding Patient Reports
Program Administration | 30 min | Practice Administrator | Q&A/open items | 

## Slide 7
Closing
Q&A
Next Steps